## Sheet1
GALAXY - BOI - Master Action Tracker
Stakeholders | BOI >> Deepak Prakash, Ankur Choudhary, Shruti
Galaxy >> Akshay, Prashant, Anil
Author | Akshay Konde
AGENDA | BOI Commvault Get Well Plan
Updated Date | 29-11-2024
ID | DISCUSSION | Status | Owner | ETA | Remarks
1 | New shift roster to be prepared with Shift Lead and Shift Engineer in every shift – Mandar – 23/11 | WIP | Akshay | 29th NOV 2024 | Shruti to confirm
2 | Process of Onboarding of new clients to be finalised and exited onboaring need to be reviwed by Sameer | WIP | Prashant | 26th NOV 2024 30th NOV 2024 | Need to take list from shruti
3 | Failure analysis need to be carried out and improvement plan to be finialised | WIP | Prashant | 2nd DEC 2024
4 | All open incidents to be reviewed and closed. Going forward, list of all open cases to be published in daily report with ageing – Shift Lead in first shift | WIP | Shift leads | 29th NOV 2024
5 | Monitoring and Alerts needs to be acted on immediately or escalated if support is needed | WIP | Shift leads | 2nd DEC 2024
6 | Roles and Responsibilities of Shift Lead and Shift Engineer to be finalized. | WIP | Anil | 29th NOV 2024
7 | Email response template to be prepared and all shift engineer to use this template for email response, All enginers need to adhere the process | WIP | Yunus/Akshay | 29th NOV 2024
8 | Daily report to be sent to all relevant stakeholders. To be sent by first shift engineer before 9am | WIP | First Shift leads | 29th NOV 2024
9 | All defunct policies to be purged by Sameer –: We can disable the policy | WIP | Prashant | 4th DEC 2024 | List of policy had been identified, once back approved we can delete
10 | Reports needed for SLA tagged clients by Sameer and SOP need to be reviewed | WIP | Prashant | 30th NOV 2024
11 | Reports from BMC to be reconciled with manual data till Dec end by first shift lead | WIP | First Shift leads/ Akshay | 2024-11-28
12 | One time backup request to be discussed for setting policies by Sameer | WIP | Prashant | 2nd DEC 2024 | Need to discussed
13 | Shift leads handover should be in tabular format with task owner | WIP | Shift leads | 29th NOV 2024
14 | Need to assign all Backup AD ID's in BMC for ticketing purpose by Mandar | WIP | Akshay | 28th NOV 2024
15 | Need to Align 3 members in night shift | WIP | Akshay | 28th NOV 2024 | Need to be reviewed by Shruti
17 | Timeline for go live of new tape library at DR site Noida | Closed | Prashant | Completed
18 | DMS Restore issue need to be fixed | WIP | Prashant | 7th DEC 2024
19 | Only approved Backup staff need to be at site of BOI: Process to be finilised and communicated | WIP | Akshay | 28th NOV 2024
20 | Backup Architecture Discussion need to scheduled ¦ 8 completed 2 pending | WIP | Akshay | 30th NOV 2024
22 | Need to track performance for backup engineer individually ¦ Bhavesh to finilised | WIP | Akshay | 30th NOV 2024
23 | Cleaning of object storage bucket across site ¦ Sameer to help Prashant | WIP | Prasant | 7th DEC 2024
24 | Worm backup failure to be escaled with Commvault and Nutanix | WIP | Anil | 30th NOV 2024